## Slide 1: LXCERT meeting 07/02/2006
  SLC5 delay impact - discussion, new plan.
  SLC4 certification status
  SLC4 roll-out planning
  SLC3 support lifetimes

## Slide 2: RHEL5 delay
RHEL5: “we do not expect a release before the end of 2006”
  (removed)
  Fermi: “told you so” (not really, but joint statement at https://www.scientificlinux.org/distributions/roadmap )
Recap: LXCERT deadline was October 2006 for “LHC” release (mostly driven by *-online groups, but *-offline probably doesn't want gcc-4 either by then (?))
SLC5 isn't going to happen before 1Q2007
SLC5 isn't going to be the “LHC startup release” ?

## Slide 3: (From Oct. meeting) Latest rumors:
  RHEL5 may come out “late” (4Q2006),
  >> 18months after RHEL3 (Sep 2003).
  (some sources: up to 27 months, tied to slower
  (9months) FedoraCore release cycle?)
  review “lockdown” timeline?
  review stability requirements per environment
  proposal: certify anyway, but carefully plan deployment.
  (impact on # of concurrent distributions -> Linux support)
    “[..] Original certification planning still holds: try to certify until the end of 2005. Currently the LCG application area software (blocking LHC experiments) and ORACLE client (blocking AB/CO) are on the critical path. [..]”
October 2005

## Slide 4: Impact
Assume: will have lots of SLC4 production systems in 2007
  No reason to wait for SLC5
  Can roll out SLC4 on all services  plan
  Need to involve GDB for Grid-wide roll-out coordination
SLC4 becomes less urgent, but more important:
  Already slippage: “end of 2005”  “end of January 06”  “after RHEL4U3”
  IT isn't the only one being late with SLC4 –
    0 (zero) pressure from experiments until now...
  But: will need to work. SLC4 would be the LHC release
    No “second chance” to get it right..

## Slide 5: Alternative: stick to SLC5 plan?
Stick to original plan, or certify a beta?
  Would have a few online farms on SLC4, rest on SLC5
  Unrealistic! SLC5 too close to LHC startup
  Little to be gained If SLC4 is around as well (have 2.6 kernel, don't foresee immediate requests for Xen)
But: SLC5 will come anyway (newer hardware support etc)
  May get used behind the scenes on hidden services
  May get used on individual laptops/desktops
  Some services will/may try to skip SLC4
  But can discuss release/certification schedules later..

## Slide 6: SLC4 status – IT view
Have:
  “onlycern” repository (JDK, ORACLE Instantclient)
  Kerberos 5 configuration
  Most of IT tools “work_for_us” (even if not fully certified)
  But: most tests done only on i386
Still need:
  Kerberos 5 + OpenSSH (“getting rid of Heimdal”)
  Formal CASTOR release
  Lots of pending updates (U3 in beta)
  64bit architectures need more tests
  Instantclient not used everywhere yet

## Slide 7: SLC4 changes(IT)
Update system goes from apt to yum on all architectures
    Apt(-rpm) is dead (0..1 active developers, no distribution)
    Yum is the future (Fedora, integrated with Red Hat tools)
    GUI: yumex (still “improving”)
Kernel updates are now fully integrated, treated as any other update by default
    too many “old” kernels otherwise
    Can turn off / configure
Other changes as announced.
    But nothing on the “physics” packages integration (yet?)

## Slide 8: SLC4 status – rest of you?
LCG: ported to SLC3/gcc-3.4, need recompile?
Experiments: waiting for dependencies?
EGEE/ETICS – just setting up build servers...
“low priority” for everybody until now?
  This ought to change...

## Slide 9: SLC4 plan (proposals)
Suggest to
wait for RHEL4 U3 release (~ 2 weeks)
  +recompilation / integration: ~mid-march.
    Will experiment code be ready by then?
Certification deadline: end of march (2006).
hand over roll-out planning & coordination to GDB (next meeting: tomorrow), discuss at HEPiX
expect: public production services (PLUS/BATCH) on SLC4 in ~October

## Slide 10: Lifetime for SLC3
Propose:
  ia64 SLC3 support: end December 2006:
    Affects CERN-IT only, experiments: “we don't care” 
  x86_64 SLC3 support: end December 2006
    Avoid widespread migration to SLC3 on 64bit HW,
    currently <15 machines (per apt/yum statistics)
  i386 SLC3 support: still end October 2007
    (in line with Fermi plans for SL, see SL roadmap )